## Sheet1
Start date |  | 2024-01-01
End date |  | TBD
Please use a max percentage of 95% for contractors that are fully devoted to MTTC.
Sub-Workstream | Res Pot | Resource | Functional Role | Planview Role | FTE/ Contractor | Onshore/ Offshore | Location | Daily Rate | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Lloyds BP |  | TBD | Project Manager | Proj Mgr.(Jr Pgrm Mgr.) FTE Onshore | FTE | Onshore | United States | 1000 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 10%
Lloyds BP |  | Jason | BEM | Sr Proj Mgr.(Pgrm Mgr.) FTE Onshore | FTE | Onshore | United States | 1000 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 10%
Lloyds BP |  | Lalit | SDC Soultion Architect | Solutions Architects FTE Onshore | FTE | Onshore | United States | 1000 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 10%
Lloyds BP |  | TBD | Business Analyst | Business Analyst FTE Onshore | FTE | Onshore | Europe | 1000 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 10%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 10%
Lloyds BP |  | Ambuj | Application Manager | Tech. Architect FTE Offshore | FTE | Onshore | United Kingdom | 1000 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 50%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 75%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 50%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 50%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 50%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 25%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 25%
Lloyds BP |  | TBD | Technical Lead (Onshore) | Tech. Analyst Contractor Onshore | Contractor | Onshore | United States | 703 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 100%
Lloyds BP |  | TBD | Technical Lead(Offshore) | Tech. Analyst Contractor Offshore | Contractor | Offshore | India | 206 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 100%
Lloyds BP |  | TBD | Developer | Developer Contractor Offshore | Contractor | Offshore | India | 206 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 1: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 2: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 100%
Lloyds BP |  | TBD | QA Lead Onshore | QA Tester Contractor Onshore | Contractor | Onshore | United States | 710 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 50%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 50%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 100%
Lloyds BP |  | TBD | QA Tester | QA Tester Contractor Offshore | Contractor | Offshore | India | 177 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 100%
Lloyds BP |  | TBD | QA Tester | QA Tester Contractor Offshore | Contractor | Offshore | India | 178 | Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 3: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 4: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 5: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 6: 100%; Please use a max percentage of 95% for contractors that are fully devoted to MTTC. Month 7: 100%